## SOW Summary
# | Client Deliverables | Deliverables | Total Hours | Retail Price $ | Discount % | Sales Investment $ | Discounted Price $
1 | Scope Cut Sheet | 1 | 1120 | 2,240.00 | 35 | 784.00 | 1,456.00
2 | Proposal - Budget ROM | 2 | 510 | 1,020.00 | 35 | 357.00 | $663.00
5 | CRM Precon Workflow | 3 | 310 | 620.00 | 35 | 217.00 | $403.00

## Deliverable 1
Feature / Module | Sub-Tasks / Description | Estimated Hours
Project Setup & Environment | Initialize backend, frontend, database (PostgreSQL/MySQL), Docker setup, CI/CD pipeline, environment variables, GitHub repo setup, Jira project setup, basic branch strategy | 16
UI / UX - Figma | Uploads, Dashboard, Analyze/View, Excel Export, Pretty Design | 40
Frontend Development | Uploads, Dashboard, Analyze/View, Excel Export, Pretty Design | 32
AI Integration | Gemini 2.5 Flash integration, prompting, scope mapping, Research | 64
Storage / Backend | S3 + SQL integration, JSON merging logic | 32
Performance & Testing | Large file handling, accuracy validation | 32
UI Enhancements | Labels, layout, and toggles | 16
Data Improvements – Design Info | Include Landscape Architect, Design Stage (CD/DD), % Complete logic | 16
Data Improvements – New Columns | Add DB & UI columns: Design % Complete, Strength of Fit, Material Type | 12
Accuracy Enhancements – Quantity Extraction | Improve extraction logic for accurate quantity detection from analysis results | 24
Accuracy Enhancements – Sheet Mapping | Map scopes to correct sheet names instead of page numbers | 12
Action Feedback – Backend (AI Feedback Loop) | Store, update, and retrieve feedback via backend APIs; integrate with sessions | 24
Action Feedback – UI | Enhance Action Feedback UI for usability & feedback visualization | 12
Scope Screenshot – Backend | Capture identified scope screenshot from drawing PDF, save in storage, link with session | 40
Scope Screenshot – UI | Display captured scope image on “View” screen with zoom/download features | 16
AI Model Fine-Tuning & Prompt Engineering | Create structured prompts, test different prompt variants for accuracy, log mispredicted scopes, iterative improvements to GEMINI 2.5 | 24
Egnyte Integration – PDF Sync | Connect to Egnyte API using access tokens; pull PDFs from designated folder(s); handle new file detection | 16
Egnyte Integration – Scheduled Analysis Jobs | Implement scheduled background jobs (e.g., Celery/APScheduler) to auto-run analysis on newly synced PDFs; log results; send status notifications | 16
Egnyte Integration – Error Handling & Logs | Add error tracking, retry logic for failed syncs, maintain Egnyte job logs for admins | 12
Heuristics - Product Types / Material / Competitor Management – DB Setup | Design DB tables for Product Types, Material Types, and Competitors; create relationships and indexes | 10
Backend – CRUD APIs | Build REST APIs (create, read, update, delete) for product types, material types, competitors; include validation & error handling | 12
Backend – Integration with AI Analysis | Update AI analysis logic to use uploaded product/material/competitor data as input context for scope detection; test with sample plans | 16
Frontend – Upload / Manage UI | Create admin UI for managing (add/edit/delete) Product Types, Material Types, Competitors; include data tables, forms, and validation | 16
Frontend – Integration with Backend | Connect UI with API endpoints; handle loading states, error messages, and success notifications | 8
Database Access & Security | Ensure proper access control (only admin or specific roles), audit logging for data changes | 8
Testing & Validation | Test full flow (UI → API → DB → AI), verify that uploaded data is correctly used by analysis engine | 8
RAG Knowledge Base Setup | Create a structured vector database (e.g., using Pinecone / FAISS / pgvector) to store pricing data, material definitions, heuristics, and project examples | 16
Document Parsing & Embedding | Convert internal documents (pricing sheets, definitions, heuristics, etc.) into embeddings; store in vector DB; maintain metadata for version control | 16
Retrieval Logic Implementation | Build retrieval layer to fetch relevant context (pricing logic, heuristics, scope definitions) before prompting Gemini 2.5 | 12
AI Prompt Augmentation | Integrate retrieved context dynamically into Gemini prompts to improve accuracy of scope detection and pricing reasoning | 16
Performance Optimization | Optimize AI analysis pipeline for large PDFs or batch processing; parallel processing, caching | 24
Testing & Evaluation | Evaluate accuracy improvement (with/without RAG), tune retrieval parameters, and benchmark response quality | 8

## Deliverable 2
Proposal - Budget ROM, Bid Quote & Public Account Web Tool
Feature / Module | Sub-Tasks / Description | Estimated Hours | Dev Total | 262
Pricing Sheet Upload | Upload Excel/CSV pricing sheet (unit prices, materials, categories); validate and store in DB | 8
AI Pricing Calculation Logic | Map extracted scopes to uploaded pricing sheet, calculate cost per scope and total plan value; expose via API | 20
Sales Proposal Generation (ROM) | Generate ROM template (Excel/PDF) with calculated pricing and total plan value for Sales dept; basic branding & layout | 12
Sales Proposal UI – Qualified View | Create Sales dashboard to view only Qualified scopes from analysis; show Scope, Quantity, Unit Price, Total Price | 12
Sales Proposal UI – Edit Capabilities | Allow Sales users to edit quantities/prices, auto-recalculate totals, and mark proposal as ready for Precon | 16
Downloadable ROM Proposal (Excel/PDF) | Build download feature for ROM proposal — generate PDF/Excel file dynamically with company branding, proposal metadata, and pricing summary | 12
Sales → Precon Handoff Logic | Implement workflow logic to push finalized Sales proposals to Precon queue (status update, audit log, notifications) | 8
UI Enhancements on View Analysis Screen | Extend existing analysis view to show Unit Price, Total Price, Department, Scope Screenshot thumbnail, Total Plan Value, and Download Proposal dropdown | 14
Testing & Validation | Verify upload → AI pricing → proposal generation → Precon transfer flow | 8
Precon Proposal Dashboard | UI for Precon team to view verified proposals from Sales; filter by project, status, and department | 10
Precon Proposal Review & Edit | Allow Precon users to view/edit verified quantities, unit prices, and material details before finalizing | 16
Detailed Bid Quote Generation | Generate Bid Quote document (Excel/PDF) with validated quantities, scope screenshots, materials, and final pricing | 16
Scope Screenshot Integration | Display captured scope thumbnails alongside line items in the Bid Quote view | 8
Downloadable Bid Quote (Excel/PDF) | Build export feature for Bid Quote — generate formatted document with validated quantities, materials, scope screenshots, pricing summary | 12
Approval & Versioning | Implement workflow for approval, version tracking, and status updates (e.g., Draft → Finalized) | 10
Audit Trail & Logs | Record all edits and approvals with timestamps and users; visible to admins | 8
Testing | Validate data accuracy, calculations, and proposal exports | 8
Public Account UI – Login/Signup | Email + OTP login/signup, passwordless auth, frontend forms, validation, API integration, responsive design | 8
Upload Plan Page & Confirmation | Upload PDF/plan functionality; file size/type validation; confirmation page; integrate with backend storage & Egnyte | 12
Access Control | Ensure public users view/download only their own project ROMs; enforce RBAC at API & UI; security testing | 12
Public Report Download | Allow download of Sales ROM (Budget) only; hide Precon Bid Quote; PDF/Excel export; proper formatting | 8
Minor Integration Adjustments | Trigger AI analysis, pricing, scope screenshot, and CRM logic for public uploads; handle async jobs, retries, error logging | 16
Testing | Full end-to-end testing: upload → analysis → ROM generation → download; test edge cases, concurrency, security, cross-browser | 8

## Deliverable 3
CRM Precon Workflow & CRM Sales Workflow
Feature / Module | Sub-Tasks / Description | Estimated Hours | Dev Total | 124
CRM Workflow Analysis | Study CRM Sales & Precon workflows; identify required fields, triggers, and data flows; document mapping with our app’s data | 12
Data Mapping & Schema Design | Map our app’s entities (Qualified Scopes, Pricing, ROM, Bid Quotes, Users) to CRM fields; design mapping logic & transformation rules | 12
API/Connector Setup | Setup connection with CRM APIs (REST/SOAP/etc.); handle authentication, rate limits, error handling | 10
Data Sync Logic – Sales Workflow | Sync qualified scopes and ROM data from our app → CRM Sales workflow; implement incremental updates & status tracking | 14
Data Sync Logic – Precon Workflow | Sync validated bid quote data from our app → CRM Precon workflow; handle approvals, attachments (screenshots, PDFs) | 14
Conflict Resolution & Error Handling | Detect and handle conflicts (e.g., updated in both systems), log errors, retry logic, notifications | 8
Testing | Test sync end-to-end (Sales + Precon workflows), validate data accuracy, ensure workflow triggers properly in CRM | 10
Notifications / Status Updates | Email or in-app notifications for job completion, ROM ready, Precon updates, public portal alerts | 20
Reporting / Analytics | Admin/Sales/Precon reports: number of plans analyzed, success rate, ROM vs Bid Quote value, AI accuracy metrics | 24

## Infra cost
# | Service | Monthly | Currency | Configuration summary
1 | Amazon EC2 | 15.038 | USD | Tenancy (Shared Instances), Operating system (Linux), Workload (Consistent, Number of instances: 1), Advance EC2 instance (t3.medium), Pricing strategy (Compute Savings Plans 3yr No Upfront), Enable monitoring (disabled), DT Inbound: Not selected (0 TB per month), DT Outbound: Not selected (0 TB per month), DT Intra-Region: (0 TB per month)
2 | Amazon EC2 | 60.298 | USD | Tenancy (Shared Instances), Operating system (Linux), Workload (Consistent, Number of instances: 1), Advance EC2 instance (t3.xlarge), Pricing strategy (Compute Savings Plans 3yr No Upfront), Enable monitoring (disabled), DT Inbound: Not selected (0 TB per month), DT Outbound: Not selected (0 TB per month), DT Intra-Region: (0 TB per month)
3 | Amazon RDS for PostgreSQL | 104.21 | USD | Storage amount (100 GB), Storage volume (General Purpose SSD (gp2)), Nodes (1), Instance Type (db.t3.medium), Utilization (On-Demand only) (100 %Utilized/Month), Deployment Option (Single-AZ), Pricing Model (OnDemand)
4 | S3 Standard | 11.5 | USD | S3 Standard storage (500 GB per month)
5 | Amazon CloudFront | 22 | USD | Data transfer out to internet (200 GB per month), Data transfer out to origin (200 GB per month), Number of requests (HTTPS) (1000000 per month)
| Total | 213.046 | USD | approx. max amount per month

## Resource and Timeline Plan
Deliverable 1 (Scope Cut Sheet) | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08
Resource | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Total | Standard Rate | Discounted Rate | Total
| Build | Build | Build | Build | Build | Build | SIT | UAT | Deploy
Project Manager | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 180 | 55 | 2 | 360
Customer Success Director | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 45 | 175 | 2 | 90
Technical Architect | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 75 | 55 | 2 | 150
UI/UX Designer | 2025-10-13: 20; 2025-10-20: 20 | 40 | 50 | 2 | 80
AI Developer | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 10 |  | 250 | 50 | 2 | 500
Full Stack Developer | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 10 | 270 | 50 | 2 | 540
QA Testing Analyst |  | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 260 | 45 | 2 | 520
SUBTOTALS | 135 | 175 | 155 | 155 | 155 | 115 | 90 | 80 | 60 | 1120 | 53 | 2 | 2240
Deliverable 2 (Proposal - Budget ROM, Bid Quote & Public Account Web Tool) | 2025-10-13: 2025-11-24; 2025-10-20: 2025-12-01; 2025-10-27: 2025-12-08; 2025-11-03: 2025-12-15; 2025-11-10: 2025-12-22
Resource | Week1 | Week2 | Week3 | Week4 | Week5 | Total | Standard Rate | Discounted Rate | Total
| Build | Build | Build | SIT & UAT | Deploy
Project Manager | 20 | 20 | 20 | 20 | 20 | 100 | 55 | 2 | 200
Customer Success Director | 5 | 5 | 5 | 5 | 5 | 25 | 175 | 2 | 50
Technical Architect | 10 | 10 | 5 | 5 | 5 | 35 | 55 | 2 | 70
AI Developer | 40 | 20 | 20 | 10 |  | 90 | 50 | 2 | 180
Full Stack Developer | 40 | 40 | 40 | 10 | 10 | 140 | 50 | 2 | 280
QA Testing Analyst |  | 40 | 40 | 20 | 20 | 120 | 45 | 2 | 240
SUBTOTALS | 115 | 135 | 130 | 70 | 60 | 510 | 56 | 2 | 1020
Deliverable 3 (CRM Precon Workflow & CRM Sales Workflow) | 2025-10-13: 2025-10-20; 2025-10-20: 2025-10-27; 2025-10-27: 2025-11-03; 2025-11-03: 2025-11-10
Resource | Week1 | Week2 | Week3 | Week4 | Total | Standard Rate | Discounted Rate | Total
| Build | Build | SIT & UAT | Deploy
Project Manager | 20 | 20 | 20 | 20 | 80 | 55 | 2 | 160
Customer Success Director | 5 | 5 | 5 | 5 | 20 | 175 | 2 | 40
Technical Architect | 10 | 10 | 5 | 5 | 30 | 55 | 2 | 60
Full Stack Developer | 40 | 40 | 10 | 10 | 100 | 50 | 2 | 200
QA Testing Analyst |  | 40 | 20 | 20 | 80 | 45 | 2 | 160
SUBTOTALS | 75 | 115 | 60 | 60 | 310 | 59 | 2 | 620